Weekly IT Updates and KPI/KRA Tracking

| Process Owner | Endpoint Management / IT Operations | Approver | Manager / Service Owner |
| --- | --- | --- | --- |
| Prepared By | Dnyaneshwar Karande | Version | 1.0 |
| Classification | Internal | Status | Handover Draft |

# 1. Purpose and Scope

To collect accurate operational data and produce a concise weekly update covering completed work, pending actions, risks, ownership and measurable progress.

| Trigger | Weekly management review, KPI/KRA cycle, project status meeting, or handover update. |
| --- | --- |
| Prerequisites | Current ticket data; asset, onboarding/offboarding, procurement, license and project trackers; reporting period; KPI definitions; owner inputs. |
| Expected output | Management-ready summary with verified metrics, actions, owners, dates and evidence links. |
| General control | Use approved request, least-privilege admin role, masked evidence, and user/owner confirmation. |

# 2. Detailed Procedure

## Step 1: Confirm reporting period and format

Set exact start/end dates, recipients, submission time and required sections.

Reuse the approved template.

Checkpoint: Reporting scope is fixed.

## Step 2: Collect source data

Gather tickets, support closures, onboarding/offboarding, assets, procurement, licenses, projects and incidents from source systems.

Do not rely only on memory or chat messages.

Checkpoint: Source list is complete.

## Step 3: Verify and clean data

Remove duplicates, confirm statuses, owners and dates, and reconcile totals between trackers.

Mark missing data instead of estimating.

Checkpoint: Metrics are supportable.

## Step 4: Calculate KPIs/KRAs

Use approved definitions for completed, pending, SLA, compliance, stock, delivery and project milestone measures.

Keep formulas consistent week to week.

Checkpoint: Numbers are comparable and reproducible.

## Step 5: Write accomplishments

Summarize outcomes such as devices delivered, enrollments completed, issues resolved, access closed, orders progressed and milestones achieved.

Use business impact, not only activity volume.

Checkpoint: Completed work is concise and meaningful.

## Step 6: List pending actions and risks

For each item include next action, owner, due date, blocker and required decision.

Separate critical/overdue items from normal follow-up.

Checkpoint: Nothing is pending without ownership.

## Step 7: Review with stakeholders

Confirm project/vendor/finance/HR dependencies with the relevant owners.

Correct discrepancies before submission.

Checkpoint: Owners agree with reported status.

## Step 8: Publish and archive

Send the final update in the approved channel.

Archive the report and source snapshot in the agreed folder.

Carry open actions into next week.

Checkpoint: Report is traceable and follow-up continues.

# 3. Validation and Completion

Reporting dates and KPI definitions are correct.

Totals reconcile with source trackers.

Pending items include owner and due date.

No sensitive personal data is unnecessarily included.

Final report and evidence are archived.

# 4. Exception and Escalation

Missing source data: mark as pending validation, assign owner and avoid invented numbers.

Conflicting status: obtain source-owner confirmation.

Critical incident or overdue dependency: escalate separately rather than waiting for weekly report.

# References

Note: Portal labels can change. Follow the current company policy, approved roles, and tenant-specific configuration if it differs from this general SOP.